## Sheet1
Date | Worksession Number | Main Painting | CP | MLS | Street Deco | D Spine deco | B Dome Deco | B Dome Font | Main lawn Font | CrossRoad | Cornor art | Graffiti
2026-08-01 | GBM 1 and inventory | Nothing |  |  |  | Nothing | Nothing | Nothing | Nothing | Nothing | Nothing | Nothing
2026-08-02 | Worksession1 + Shopping Trip 1 | Painting taped and gridding | L rod Structure | Nothing | Complete 5 to 7 selected hard SD (atleast skecthing)
2026-08-03 | Worksession2
2026-08-04 | Worksession3 | Sketching |  | L rod Structure
2026-08-05 | Worksession4
2026-08-06 | Worksession5
2026-08-07 | Worksession6 |  | PVC pipe Structures Complete
2026-08-08 | Worksession7 + Independence day work 1
2026-08-09 | Worksession8 + Independence day work 2
2026-08-10 | Worksession9 + Independence day work 3 |  |  |  | Anything if needed acc to attendence | Complete
2026-08-11 | Worksession10 + Independence day work 4
2026-08-12 | Worksession11 + Independence day work 5
2026-08-13 | Worksession12 + Independence day work 5
2026-08-14 | Worksession13 + Installations and rangoli | Painting Castle and Trees
2026-08-15 | No WorkSession
2026-08-16 | Worksession14 |  |  | PVC pipe Structure Complete + Sword made seperatly
2026-08-17 | Worksession15
2026-08-18 | Worksession16
2026-08-19 | Worksession17
2026-08-20 | Worksession18
2026-08-21 | Worksession19 |  | Tail Part Using Carboard and head (parrallely) Complete
2026-08-22 | Worksession20 + Shopping Trip 2 |  |  |  |  | Nothing
2026-08-23 | Worksession21
2026-08-24 | Worksession22
2026-08-25 | Worksession23
2026-08-26 | Worksession24
2026-08-27 | GBM 2 for inductions
2026-08-28 | Inductions
2026-08-29
2026-08-30 |  |  | Crystals using cardboard (Crew can work on this)
2026-08-31 | Worksession25
2026-09-01 | Worksession26
2026-09-02 | GBM 3 (first Crew GBM) |  |  |  | Complete
2026-09-03 | Worksession27 | [5 empty] | Crew Starts working on this in parallel
2026-09-04 | Worksession28 |  | Stuffing main body + Head parallely |  |  |  | Themocol rectangles cutting | Nothing untill enough people then start cutting themocol | Made in 2 ws whenever free enough | Nothing | If time and looks feasable | Nothing
2026-09-05 | Worksession29
2026-09-06 | Worksession30
2026-09-07 | Worksession31
2026-09-08 | Worksession32 | [5 empty] | Sketching Dragons
2026-09-09 | Worksession33 |  | Legs and Ground crystal + Head parallely | Main body armor
2026-09-10 | Worksession34 + Shopping Trip 3
2026-09-11 | Worksession35 | Painting Sky background montains and river
2026-09-12 | Worksession36
2026-09-13 | Worksession37 |  |  |  | Nothing
2026-09-14 | Worksession38
2026-09-15 | Worksession39 |  | Wings + Head parallely
2026-09-16 | Worksession40
2026-09-17 | Worksession41
2026-09-18 | Worksession42 | [6 empty] | Drawing and cutting font
2026-09-19 | Worksession43
2026-09-20 | Worksession44 |  |  | Legs and arms
2026-09-21 | Worksession45 | Painting Boundary
2026-09-22 | Worksession46
2026-09-23 | Worksession47 | [6 empty] | Painting
2026-09-24 | Worksession48 + Shopping Trip 4 | [5 empty] | Painting Dragons
2026-09-25 | Worksession49 | Finishing and mistake fixing | Buffer
2026-09-26 | Worksession50
2026-09-27 | Worksession51
2026-09-28 | Worksession52
2026-09-29 | Worksession53
2026-09-30 | Worksession54
2026-10-01 | MIDSEMS | Nothing | Nothing | Nothing |  |  |  | Nothing
2026-10-02
2026-10-03
2026-10-04
2026-10-05
2026-10-06 | [8 empty] | Nothing
2026-10-07
2026-10-08 | [9 empty] | Complete
2026-10-09
2026-10-10
2026-10-11
2026-10-12
2026-10-13
2026-10-14 | GBM 4
2026-10-15 | Worksession55 |  | Paper Mache for skin and carboard pieces for detail | Head and cape plus sword attached |  |  |  | Painting | Led whenever time
2026-10-16 | Worksession56
2026-10-17 | Worksession57 + Shopping Trip 5 if needed
2026-10-18 | Worksession58 | [10 empty] | Primer and bg
2026-10-19 | Worksession59
2026-10-20 | Worksession60
2026-10-21 | Worksession61 | [10 empty] | Sketching and masking
2026-10-22 | Worksession62 | [5 empty] | Nothing | Nothing |  | Nothing
2026-10-23 | Worksession63
2026-10-24 | Worksession64 | [10 empty] | Spray Painting
2026-10-25 | Worksession65
2026-10-26 | Worksession66 | [10 empty] | Installations
2026-10-27 | Worksession67
2026-10-28 | Installations
2026-10-29 | Installations